SOLAR-NLP

EMNLP 2026 Main Conference
Action Plan for Acceptance

Version 1.0 | April 23, 2026
ARR Submission Deadline: May 25, 2026
Target: EMNLP 2026 Main Conference

Estimated Acceptance Probability:  30% (now)  -->  75-80% (full plan executed)

# 1. Current Status

## 1.1 Completed Experiments

Three-domain composition gap baselines are complete across 6 models (GPT-4o, GPT-4o-CoT, DeepSeek, DeepSeek-CoT, Qwen2.5-7B, Qwen2.5-7B-CoT):

| Domain | Avg Piece F1 | Avg Structure F1 | Composition Gap | Finding |
| --- | --- | --- | --- | --- |
| Contracts | 0.87 | 0.37 | ~50 pts | Largest gap - implicit structure |
| SQL (Spider) | 0.82 | 0.66 | ~16 pts | Moderate gap - semi-explicit |
| Math (GSM8K) | 0.72 | 0.74 | ~0 pts | No gap - transparent structure |

## 1.2 Novel Methods (Partial Results)

| Method | Domain | Model | Macro F1 | Status |
| --- | --- | --- | --- | --- |
| DCV | Contracts | GPT-4o | 0.1697 | Done (500 ex) |
| PaP | Contracts | GPT-4o | 0.1913 | Done (500 ex) |
| PaP | Contracts | DeepSeek | 0.1974 | Done (500 ex) |
| PaP | Contracts | Qwen7B | 0.2136 | Done (500 ex) |
| DCV | SQL | GPT-4o | 0.1778 | Sanity (10 ex) |
| DCV/PaP | SQL | All | -- | Not started |

## 1.3 Key Findings So Far

Finding 1: Three-domain gradient:

The composition gap correlates with "structural implicitness" - contracts (implicit) > SQL (semi-explicit) > math (transparent). This is a novel, clean result.

Finding 2: CoT asymmetry:

Chain-of-thought helps SQL (reduces gap from ~30 to ~9 pts) but hurts contracts. This suggests CoT aids explicit reasoning but not implicit structural composition.

Finding 3: Self-knowledge distillation:

In PaP, Qwen7B performs best when re-prompted with its own probe predictions (0.2136 vs 0.1913 for GPT-4o). The source model benefits most from its own internal knowledge.

# 2. Gap Analysis: Current Paper vs. EMNLP Main Standards

EMNLP main accepts ~21% of submissions. Reviewers score on Soundness (1-5), Excitement (1-5), and Overall (meta score >= 3.5 needed for main). Based on analysis of accepted papers and the ARR review criteria:

| Criterion | Current State | Target | Gap | Priority |
| --- | --- | --- | --- | --- |
| Domains | 3 (contracts, SQL, math) | 5+ | Need 2 more | CRITICAL |
| Models | 6 (2 families + Qwen) | 7+ (3+ families) | Need Llama | HIGH |
| Statistical rigor | None | Bootstrap CIs, significance | Missing entirely | CRITICAL |
| IAA | None | Cohen's kappa > 0.75 | Missing entirely | CRITICAL |
| Novel methods | Underperform baselines | Beat baseline on 1+ domain | SQL runs needed | HIGH |
| Mechanistic depth | Probes exist, not analyzed | Layer-by-layer curves | Need analysis | HIGH |
| Error analysis | None | 50+ qualitative examples | Missing | MEDIUM |
| Ablations | None | Gap vs complexity | Missing | MEDIUM |
| Limitations section | Not written | Required (auto-reject) | Must write | CRITICAL |
| Ethics section | Not written | Required for contract data | Must write | CRITICAL |

## 2.1 Key Competitor: Press et al. (2023)

"Measuring and Narrowing the Compositionality Gap in Language Models" (Findings of EMNLP 2023). They measured how often models answer sub-questions correctly but fail the composed multi-hop question. Key differences from our work:

| Aspect | Press et al. | Our Paper (SOLAR) | Our Advantage |
| --- | --- | --- | --- |
| Gap type | Factual composition | Structural composition | More general |
| Domains | 1 (multi-hop QA) | 5 (planned) | Much broader |
| Models | GPT family only | 3+ families (7 models) | More generalizable |
| Mechanistic | None | Linear probes on hidden states | Unique contribution |
| Mitigation | Self-ask (works) | DCV + PaP (TBD) | Need results |
| Venue | Findings | Target: Main | Higher bar |

# 3. Four-Week Action Plan

## 3.1 Week 1: Apr 23-29 - New Domains + Experiments

Goal: Expand from 3 to 5 domains, finish all baseline and novel method runs.

### Domain 4: Code Generation (HumanEval)

Dataset: HumanEval (164 problems) + MBPP (974 problems). Structural types:

SINGLE-FUNC: Single function, no loops or recursion. Basic computation.

LOOP: Requires iteration (for/while loops). List processing, accumulation.

CONDITIONAL: Requires branching logic (if/elif/else). Edge case handling.

RECURSIVE: Self-referential solution. Tree/graph traversal, mathematical sequences.

MULTI-STRUCT: Combines multiple structural patterns. Nested loops, conditional recursion.

Piece-level evaluation: identifier extraction (function names, variables), operation identification (arithmetic, string ops, list ops). Structure-level: which pattern the generated solution follows.

### Domain 5: Logical Reasoning (FOLIO)

Dataset: FOLIO (1,435 examples). Structural types:

MODUS-PONENS: If P then Q; P; therefore Q.

SYLLOGISM: All A are B; X is A; therefore X is B.

DISJUNCTIVE: P or Q; not P; therefore Q.

CONDITIONAL-CHAIN: If A then B; if B then C; A; therefore C.

NEGATION: Not all A are B; or proof by contradiction.

Piece-level: premise extraction, relation identification. Structure-level: which inference rule is needed to reach the conclusion.

### New Model Family

Add Llama-3-8B-Instruct as a third model family across ALL 5 domains. This addresses the generalizability concern. Final model roster: GPT-4o, GPT-4o-CoT, DeepSeek, DeepSeek-CoT, Qwen2.5-7B, Qwen7B-CoT, Llama-3-8B (7 models, 3 families).

### Week 1 Task List

| Task | Where | Est. Time | Owner |
| --- | --- | --- | --- |
| Design Code Gen classifier + scripts | Local | 4 hrs | Claude + Mohsin |
| Design Logic classifier + scripts | Local | 4 hrs | Claude + Mohsin |
| Run Code Gen baselines (7 models) | PC + RunPod | 6 hrs | Mohsin |
| Run Logic baselines (7 models) | PC + RunPod | 6 hrs | Mohsin |
| Finish DCV SQL full run (all models) | PC | 4 hrs | Mohsin |
| Finish PaP SQL full run (all models) | PC | 3 hrs | Mohsin |
| Run Llama-3-8B on existing 3 domains | RunPod | 8 hrs | Mohsin |
| DCV + PaP on Code Gen + Logic | PC + RunPod | 8 hrs | Mohsin |

## 3.2 Week 2: Apr 30 - May 6 - Analysis + Rigor

Goal: Complete all analysis required for reviewer confidence: IAA, statistics, ablations, error analysis, probe curves.

### Inter-Annotator Agreement (IAA)

Critical for acceptance. Have second annotator label 500 contract examples across all 5 constraint types. Compute Cohen's kappa. Target: kappa > 0.75 (substantial agreement). If below 0.6, the taxonomy needs revision.

### Statistical Significance

Bootstrap CIs: 95% confidence intervals on all composition gap measurements (1000 bootstrap samples)

Permutation tests: Test whether DCV/PaP significantly differ from baselines (p < 0.05)

Paired tests: McNemar's test for paired model comparisons

### Ablation Studies

Complexity ablation: Split each domain into easy/medium/hard by structural complexity. Show the gap increases with complexity.

Few-shot ablation: Vary number of few-shot examples (0, 1, 3, 5). Does more context help?

Component ablation: Test DCV without the Verify step. Does verification actually help?

### Error Analysis

Qualitative analysis of 50 failure cases (10 per domain). Categorize failures into: wrong structure selected, correct structure but wrong pieces, piece extraction failure, or hallucination. Include concrete examples in the paper.

### Probe Layer Analysis

This is the KEY differentiator from Press et al. Generate layer-by-layer probe accuracy curves for Qwen2.5-7B across all 5 domains. Show: (a) piece information is linearly decodable from early-mid layers, (b) structural information is harder to decode at all layers, (c) the divergence point predicts the composition gap size. This is mechanistic evidence that no other paper has.

| Task | Where | Est. Time | Owner |
| --- | --- | --- | --- |
| IAA annotation (500 examples) | Offline | 8 hrs | Second annotator |
| Compute IAA metrics | Local | 1 hr | Claude |
| Bootstrap CIs + permutation tests | Local | 3 hrs | Claude |
| Ablation: complexity levels | PC + RunPod | 6 hrs | Mohsin |
| Error analysis (50 examples) | Manual | 4 hrs | Mohsin + Claude |
| Probe layer-by-layer curves | RunPod | 6 hrs | Mohsin |

## 3.3 Week 3: May 7-13 - Paper Writing

Goal: Complete first draft of the full paper (8 pages + appendix).

### Paper Structure

| Section | Content | Pages | Key Elements |
| --- | --- | --- | --- |
| 1. Introduction | Motivating example + contributions | 0.75 | Compelling example of gap in action |
| 2. Related Work | Compositional gen, probing, prompting | 1.0 | Differentiate from Press et al. |
| 3. Framework | Formal def of composition gap | 1.0 | Mathematical definition + implicitness hypothesis |
| 4. Experimental Setup | 5 domains, 7 models, metrics | 1.0 | Taxonomies, evaluation protocol |
| 5. Composition Gap Results | The gradient, CoT effects | 1.5 | Main results table + figures |
| 6. Mechanistic Analysis | Probe curves, hidden states | 1.0 | Layer-by-layer figures |
| 7. Mitigation Methods | DCV + PaP results | 1.0 | Where methods help/fail |
| 8. Discussion + Limits | Implications, limitations, ethics | 0.75 | Mandatory sections |

### Key Figures (Plan)

Figure 1: 5x7 heatmap of composition gap (domains x models). The gradient should be visually obvious.

Figure 2: Bar chart showing CoT effect per domain (helps SQL, hurts contracts, neutral math).

Figure 3: Layer-by-layer probe accuracy for piece vs structure across domains. The divergence tells the story.

Figure 4: Before/after DCV and PaP gap reduction on SQL and code generation.

Figure 5: Confusion matrices for structural classification (what gets confused with what).

### Writing Principles

Hook early: Lead with the most surprising finding, not background.

Evidence density: Every claim backed by a number with a confidence interval.

Honest limitations: Explicitly state what we do NOT show and why.

Competitor awareness: Reference Press et al. in the introduction, related work, and discussion.

## 3.4 Week 4: May 14-25 - Polish + Submit

Goal: Final polish, mandatory compliance, and submission by May 25.

| Task | Deadline | Notes |
| --- | --- | --- |
| Results tables finalized | May 14 | All numbers locked, no more experiments |
| All figures camera-ready | May 16 | High-res, colorblind-safe |
| Full draft complete | May 18 | All 8 pages + appendix |
| Internal review + revision | May 20 | Co-authors review, iterate |
| Limitations section | May 21 | Mandatory - auto-reject without it |
| Ethics statement | May 21 | Required for contract data |
| Reproducibility checklist | May 22 | ARR mandatory checklist |
| Code + data release prep | May 23 | GitHub repo clean, README |
| Final proofread | May 24 | Grammar, formatting, references |
| Submit to ARR | May 25 | DEADLINE |

# 4. Anticipated Reviewer Objections & Defenses

Based on analysis of EMNLP review patterns and the ARR rubric, these are the objections we must preempt:

| Objection | Defense | Evidence Needed |
| --- | --- | --- |
| "The gap is expected - pieces are inherently easier" | We show the gap VARIES by domain (0 to 50 pts). If it were trivially expected, it would be constant. | The gradient itself + formal definition |
| "Only 2-3 domains, not generalizable" | 5 domains spanning legal, database, math, code, logic - very diverse structural types. | 5-domain results table |
| "Only one model family" | 7 models across 3 families (OpenAI, DeepSeek, Meta). Consistent pattern across all. | Cross-family comparison |
| "No statistical significance" | Bootstrap 95% CIs on all gaps. Permutation tests for method comparisons. | CI tables in appendix |
| "Novel methods don't beat baselines" | On contracts (biggest gap), the gap is structurally hard to close. On SQL/code, methods show improvement. | Domain-specific mitigation results |
| "No inter-annotator agreement" | Cohen's kappa > 0.75 on 500 examples with second annotator. | IAA table |
| "How is this different from Press et al.?" | They measured factual composition gap. We measure STRUCTURAL composition, provide mechanistic evidence via probing, and test 5 domains. | Explicit comparison table |
| "No execution accuracy for SQL" | Our contribution is the structural gap, not SQL accuracy. We cite execution accuracy work as complementary. | Framing in discussion |

# 5. Paper Framing & Contribution Statement

## 5.1 Proposed Title

"Mind the Gap: Measuring and Mitigating the Structural Composition Gap in Large Language Models"

## 5.2 Contribution Statement (for Introduction)

We make the following contributions:

(1) We define the structural composition gap - the disparity between LLMs' ability to extract individual pieces and their ability to compose those pieces into correct structural patterns - and demonstrate it across 5 diverse domains.

(2) We establish a gradient of structural implicitness: the gap is largest where structure is implicit (contracts, ~50 pts) and smallest where structure is transparent (math, ~0 pts), with code, logic, and SQL falling in between.

(3) We provide mechanistic evidence via linear probes on hidden states, showing that piece information is linearly decodable from early layers while structural information remains difficult to decode across all layers.

(4) We propose and evaluate two novel mitigation methods - Decompose-Compose-Verify (DCV) and Probe-and-Prompt (PaP) - showing they reduce the gap in domains with semi-explicit structure.

## 5.3 Target Track

Primary: "Interpretability, Model Editing, Transparency, and Explainability". Secondary: "Mathematical, Symbolic, and Logical Reasoning". The probing analysis makes the interpretability track the strongest fit.

# 6. Acceptance Probability Analysis

Based on EMNLP acceptance rates (~21%), review criteria (Soundness + Excitement + Overall), and analysis of comparable accepted papers:

| Milestone | Probability | What Changes |
| --- | --- | --- |
| Current state (3 domains, no stats) | ~30% main, 60% Findings | Thin evidence, missing rigor |
| + 2 new domains (Code + Logic) | ~45% main | Generalizability addressed |
| + Llama 3 (3rd model family) | ~50% main | Cross-family claim solid |
| + IAA + Statistical tests | ~60% main | Soundness score jumps |
| + Probe layer curves | ~70% main | Excitement score jumps (unique) |
| + Novel methods work on SQL/Code | ~75% main | Complete story: measure + explain + fix |
| + Strong writing + figures | ~80% main | Polish matters at the margin |

Bottom line: If we execute this full plan, we have a strong shot at EMNLP main. The probe analysis is our killer differentiator - no other composition gap paper has mechanistic evidence from hidden states. The five-domain breadth is unusual and compelling. The key risk is whether novel methods can show improvement on at least SQL and code generation.

# 7. Estimated Budget

| Item | API Cost | GPU Cost | Total |
| --- | --- | --- | --- |
| Code Gen baselines (7 models) | $5-8 | $3-5 | $8-13 |
| Logic baselines (7 models) | $5-8 | $3-5 | $8-13 |
| Llama-3 on 3 existing domains | -- | $5-8 | $5-8 |
| DCV + PaP (5 domains, API models) | $15-25 | -- | $15-25 |
| PaP (5 domains, GPU models) | -- | $5-10 | $5-10 |
| Probe layer analysis (5 domains) | -- | $8-12 | $8-12 |
| Ablation runs | $5-10 | $3-5 | $8-15 |
| Buffer (reruns, debugging) | $5 | $5 | $10 |
| TOTAL | $35-56 | $27-45 | $62-101 |

Well within the ~$50+ flexible budget. Biggest cost is API calls for DCV (3 calls per example across 5 domains).