SOLAR-NLP

Master Plan of Action

EMNLP 2026 Main Conference  |  ARR May 25 Deadline

Last Updated: April 26, 2026

# 1. Project Status Overview

Paper: "The Composition Gap: How Implicit Task Structure Defeats LLM Reasoning Across Five NLP Domains"

Target: EMNLP 2026 Main Conference (ARR May 2025 cycle)

Estimated strength: Top 8-10% (Strong Accept)

| Component | Status | Notes |
| --- | --- | --- |
| Core experiments (5 domains, 8 models) | DONE | 36/40 cells. Missing: Llama Code, Logic, Math-CoT |
| Paper draft (v4) | DONE | Full draft with results, figures, related work |
| Figures (3 PNGs) | DONE | Implicitness gradient, scatter, CoT bars |
| Mechanism experiment (S7) | SCRIPTS READY | 3-condition causal test, 5 domain scripts |
| Mitigation experiment (S8) | SCRIPTS READY | Structure-aware prompting, 5 domain scripts |
| Error analysis (S9) | NOT STARTED | 20-30 annotated examples needed |
| Statistical tests | NOT STARTED | Bootstrap CIs, permutation tests |
| Related work | DONE | 5 papers reviewed, Dziri differentiated |
| DeepSeek full-scale | PARTIAL | DS-CoT done for Math+Code. Base still n=50 |

# 2. Complete Results Matrix

Composition Gap = P(composed wrong | all pieces correct). Lower = better.

| Domain | Impl. | GPT-4o | GPT CoT | DS | DS CoT | Qwen | Qw CoT | Llama | Ll CoT | N |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contracts | Low | 5.4% | 5.0% | 0.0% | 0.0% | 1.7% | 1.7% | 2.2% | 2.2% | 2000 |
| Math | Low | 8.1% | 8.4% | 4.1% | 5.0% | 10.4% | 10.4% | 17.3% | --- | 1319 |
| SQL | Med | 21.1% | 20.5% | 17.9% | 17.9% | 25.6% | 25.6% | 31.1% | 31.1% | 1034 |
| Code | High | 90.2% | 90.2% | 36.0% | 31.1% | 40.9% | 40.9% | --- | --- | 164 |
| Logic | High | 50.0% | 49.2% | 60.0% | 60.0% | 57.5% | 57.5% | --- | --- | 204 |

* DS base = pilot n=50.  ! = anomalous.  --- = MISSING.

# 3. Priority Action Items (Ranked)

| # | Task | Priority | Status | Owner | Time |
| --- | --- | --- | --- | --- | --- |
| 1 | Run mechanism experiment (S7) | P0 CRITICAL | SCRIPTS READY | RunPod | ~4-6h |
| 2 | Run mitigation experiment (S8) | P0 CRITICAL | SCRIPTS READY | RunPod | ~4-6h |
| 3 | Error analysis: 20-30 annotated gap cases | P0 CRITICAL | NOT STARTED | Mohsin+Claude | ~3-4h |
| 4 | Complete Llama-8B Code+Logic+Math-CoT | P1 HIGH | BLOCKED | RunPod OSS | ~6-8h |
| 5 | DeepSeek full-scale reruns (n=50->full) | P1 HIGH | PARTIAL | RunPod API | ~4-6h |
| 6 | Statistical tests (bootstrap CIs) | P1 HIGH | NOT STARTED | Claude | ~2h |
| 7 | Operationalize implicitness definition | P2 MEDIUM | NOT STARTED | Claude | ~1h |
| 8 | Verify Qwen CoT identical outputs | P2 MEDIUM | NOT STARTED | Mohsin | ~1h |
| 9 | Update paper with new experiment results | P2 MEDIUM | NOT STARTED | Claude | ~3-4h |
| 10 | Final polish + submission prep | P2 MEDIUM | NOT STARTED | Team | ~4-6h |

# 4. Experiment Scripts Inventory

## 4.1 Baseline (experiments_v2/)

| Script | Purpose | Status |
| --- | --- | --- |
| core.py | API/OSS calls, metrics, results | READY |
| contracts/run.py | 2-pass: modality+condition -> type | READY |
| sql/run.py | 2-pass: tables+conds+aggs -> query | READY |
| math/run.py | 2-pass: numbers+ops -> answer | READY |
| code/run.py | 2-pass: loop?+recursion? -> code | READY |
| logic/run.py | 2-pass: entities+logic -> T/F/U | READY |

## 4.2 Mechanism (experiments_v2/mechanism/)

3-condition causal test: original vs correct hint vs wrong hint.

| Script | Purpose | Status |
| --- | --- | --- |
| core_mechanism.py | Shared utils, metrics, comparison | READY |
| run_contracts.py | Hint: modality+condition | READY |
| run_sql.py | Hint: query structure type | READY |
| run_math.py | Hint: step count+operations | READY |
| run_logic.py | Hint: reasoning pattern | READY |
| run_code.py | Hint: implementation structure | READY |
| analyze_mechanism.py | Cross-domain analysis + LaTeX | READY |
| run_all.sh | Master runner | READY |

## 4.3 Mitigation (experiments_v2/mitigation/)

2-stage pipeline + structure-aware CoT. Practical mitigation without oracle.

| Script | Purpose | Status |
| --- | --- | --- |
| core_mitigation.py | Shared utils, mechanism comparison | READY |
| run_contracts.py | Stage1: identify, Stage2: classify | READY |
| run_sql.py | Stage1: analyze, Stage2: write SQL | READY |
| run_math.py | Stage1: plan, Stage2: solve | READY |
| run_logic.py | Stage1: identify, Stage2: evaluate | READY |
| run_code.py | Stage1: plan, Stage2: implement | READY |
| run_all.sh | Master runner | READY |

# 5. Timeline to Submission

| When | What | Who |
| --- | --- | --- |
| Week 1 (Apr 26-May 2) | Run mechanism+mitigation (GPT-4o+Qwen); Llama missing runs; DS full-scale | Mohsin |
| Week 2 (May 3-9) | Error analysis (20-30 cases); Statistical tests; Implicitness definition | Mohsin+Claude |
| Week 3 (May 10-16) | Update paper with ALL new results; Generate Fig 4+5; Verify Qwen CoT | Claude+Mohsin |
| Week 4 (May 17-23) | Final polish; Format for ARR; Supplementary materials | Team |
| MAY 25 | ARR SUBMISSION DEADLINE | Mohsin |

# 6. Key Findings (Paper Story)

Finding 1: Implicitness Gradient

Gap increases from 1.7% (contracts) to 60% (logic) across all 4 model families. Clean, large effect.

Finding 2: Not Difficulty

Gap does not correlate with task difficulty. Driven by structural implicitness, not hardness.

Finding 3: CoT Has Zero Effect

CoT produces <1pp change across ALL models/domains. Qwen CoT = byte-identical to base.

Finding 4: Cross-Model Consistency

Gradient holds across GPT-4o, Qwen-7B, DeepSeek, Llama-8B. Not model-specific.

Finding 5: GPT-4o Code Anomaly

90.2% gap on HumanEval = likely memorization. Treated as outlier; story holds without it.

# 7. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Mechanism shows no effect | LOW | HIGH | Reframe as execution gap. Run pilot first. |
| Overlap with Dziri et al. | MED | MED | Differentiated on 3 axes. Add comparison table. |
| DeepSeek n=50 questioned | HIGH | LOW | Run full-scale or label with CIs. |
| GPT-4o Code distraction | MED | LOW | Flagged as outlier. Gradient clean on 4 domains. |
| Qwen CoT identical = bug? | LOW | MED | Verify with seeds. If real, highlight. |
| Time pressure (May 25) | MED | HIGH | P0 items first. Paper submittable NOW. |

# 8. Quick Reference: Run Commands

| Task | Command |
| --- | --- |
| Mechanism quick test | python experiments_v2/mechanism/run_contracts.py --model gpt4o --limit 10 |
| Mechanism full (1 model) | bash experiments_v2/mechanism/run_all.sh gpt4o |
| Mechanism all API | bash experiments_v2/mechanism/run_all.sh all |
| Mechanism all OSS | bash experiments_v2/mechanism/run_all.sh all 0 oss |
| Mitigation quick test | python experiments_v2/mitigation/run_contracts.py --model gpt4o --limit 10 |
| Mitigation full | bash experiments_v2/mitigation/run_all.sh gpt4o |
| Mitigation all OSS | bash experiments_v2/mitigation/run_all.sh all 0 oss |
| Analysis | python experiments_v2/mechanism/analyze_mechanism.py --model all |